## Sheet1
Test Planner and Tracker |  |  | Team - 3 | Sanchit Jalan Karan Nijhawan Palle Sreeja Manda Vaishnavi Reddy
Test No. ID | Related Use case | Pre-conditions | Test Description (steps) | Expected Outcome | R1 Outcome (color code cell background) | Comments (if test case failed) | R2 Outcome (color code cell background) | Comments (if test case failed)
1 | Verify Login Functionality | User details are in the database already. | 1. Navigate to the login page. | User is successfully logged in and redirected to the main dashboard.
2 | Verify Signup Functionality |  | 1. Navigate to the signup page. | User account is successfully created, and the user is redirected to the main dashboard. |  |  |  |  | Done
3 | Verify Error Message for Invalid Credentials | User details are in the database already. | 1. Navigate to the login page. | User receives an appropriate error message indicating invalid credentials. |  |  |  |  | In Progress
4 | Verify Project Creation with Valid Details |  | 1. Navigate to the create project page. | A new project is successfully created and added to the user's project list. |  |  |  |  | Not Done
5 | Verify Error Message for Empty Project Name |  | 1. Navigate to the create project page. | User receives an error message indicating that the project name field is required. |  |  |  |  | R2 Work
6 | Verify Cancel Button Functionality |  | 1. Navigate to the create project page. | User is redirected back to the main dashboard without creating a new project. |  |  |  |  | Design Change
7 | Verify Project Selection | There is atleast one project present. | 1. Click on a project from the project list | The selected project is opened and displayed.
8 | Verify Project Details Display |  | 1. Open a project. | Project details such as name, Images, path , number of frames they have are displayed.
9 | Verify Navigation Back to Dashboard | Dashboard is already created. | 1. Click on the back button or project list. | User is redirected back to the main dashboard.
10 | Verify Project Deletion | There is atleast one project present. | 1. Open the project settings or options. | The project is successfully deleted, and the user is redirected to the main dashboard. |  | ¦
11 | Verify Image Import Functionality |  | 1. Locate the import button. | The selected 360 image is successfully imported and displayed in the project.
12 | Verify Error Message for Unsupported File Format |  | 1. Locate the import button. | User receives an error message indicating that the selected file format is not supported.
13 | Verify Cancel Button Functionality |  | 1. Click on the cancel import button. | The import process is canceled, and the user remains on the project page without any changes.
14 | Verify Image Preview after Import, further interaction |  | 1. Verify that the imported image is displayed in the project interface. | The imported 360 image is displayed correctly, ready for
15 | Verify Interface for Viewing 360-Degree Image. | There is atleast one image in the project. | 1. Open the project with the imported 360-degree image. | The interface for viewing the 360-degree image is displayed.
16 | Verify Left Movement Functionality | There is atleast one image in the project. | 1. Utilize the provided controls to move the image left. | The image moves smoothly to the left.
17 | Verify Right Movement Functionality | There is atleast one image in the project. | 1. Utilize the provided controls to move the image right. | The image moves smoothly to the right.
18 | Verify UI for Drawing Annotation Boxes | There is atleast one image in the project. | 1. Open the project with the imported 360-degree image. | The UI for drawing annotation boxes is displayed.
19 | Verify Drawing Annotation Box Functionality | There is atleast one image in the project. | 1. Use the drawing tools to draw an annotation box on the image. | An annotation box is successfully drawn on the image.
20 | Verify Labeling Annotation Box | There is atleast one image in the project. | 1. Click on the annotation box to select it. 2. Add a label to the selected annotation box. | The label is successfully added to the selected annotation box.
21 | Verify Export Functionality | There is atleast one image in the project. | 1. Click on the export Button 2. Desired files will be exported | Exported files will be downloaded as required
22 | Verify Import Labels Functionality | There is atleast one project present. | 1. Enter Label Name 2. Select Label Colour and press save Button | Label will be created and will be added to Existing Labels
23 | Box drawing hovering | Box drawing should be done | 1.Hover over the annotation. | Corresponding Label would be shown on screen
24 | Segmentation drawing hovering | Segmentation drawing should be done | 1.Hover over the annotation. | Corresponding Label would be shown on screen
25 | Segmentation drawing deleting | Segmentation drawing should be done | 1.Select the annotation using mouse right click. 2. Press Delete button | Corresponding annotation will be deleted
26 | Box drawing deleting | Box drawing should be done | 1.Select the annotation using mouse right click. 2. Press Delete button | Corresponding annotation will be deleted
27 | Verify Filter functionality | Images should be there | 1. Select filter button and then select labels to be filtered out and press submit . | Corresponding images will be filtered out for specific labels
28 | Verify Sort Functionality | Images should be there | 1. Click on sort button | Corresponding images will be sorted in ascending order based on image names.